Project action plan

LIFE project: Social Media Potential for Building Meaningful Connections supervisor(s): Erik Ehasoo

team members: Geily Nurmeots, Ivan Strigin, Ilea Liidia Peckham, Helena Jõgi, Julia Sidorova, Anneli Põldaru, Lisandra Kask, Sifat-E- Afzal, Isabella Shuxin Savela, Sohrab Quraishi, Maria Miriame Russo, Eva Dyachuk

| Tasks | Deadline | Student(s) responsible |
| --- | --- | --- |
| 1. Finding friends who have met online 2. Brainstorming interview questions (2+) | 23.02 | All |
| 1. Preparing interviews 2. Scheduling interviews | 2.03 | SA, ML, GJ, IS, HI |
| Collecting theoretical material | 2.03 | IE |
| 1. Conducting 3 interviews per pair (recording if possible) 2. Transcribing interviews | 16.03 | SA, ML, GJ, IS, HI |
| Writing the theoretical overview | 16.03 | IE |
| Highlighting findings from interviews/materials, making notes, preparing for the presentation | 23.03 | All |
| Completing the mid-term report. Team leader sends it to elu@tlu.ee | 21.03 | Mango |
| Completing the mid-term report. Team leader sends it to elu@tlu.ee | 23.03 | Avocado |
| Finishing the mid-term presentation | 28.03 | All (in teams) |
| “Speculative science fiction workshop” by Prof. Katrin Tiidenberg.  April 6th at 13.00 in TLU Silva building, room S-233. | 6.04 | All |
| Workshop followup | 13.04 | All |
| Idea pitching | 20.04 | All |
| Prototype/mockup designing | 27.04 | All (in pairs) |
| Preparing the final presentation and project portfolio. Meeting in TLU, Mare building, ELU room | 4.05 | All |
| Finalizing the final presentation and project portfolio | 11.05 | All |
| Publish blog post | 11.05 | Eva |
| Submitting project portfolio (including self-reflective reports) | 12.05 | Erik |
| Final presentation | 16.05 | All |